## TM1
BI/MI TM1
Project Plan: | Work Breakdown Structure View
Start Date: | 2013-10-21
End Date: | 2014-03-06
S.No. | Tasks | Responsibility |  | Number of working days | Start | End | % Complete | Dependency | Actual Start | Actual End | Remarks | Remarks
|  | PH | TCS
1.1 | Process
1.1.1 | Communication Process | a |  | 5 | 2013-10-21 | 2013-10-25
1.1.2 | Project Delivery Model | a |  | 5 | 2013-10-21 | 2013-10-25 | 100%
1.3 | Requirements gathering and Analysis
1.3.1 | Preparation |  | a | 14 | 2013-10-28 | 2013-11-14
1.3.2 | BRSD Preparation |  | a | 6 | 2013-11-11 | 2013-11-18
1.3.3 | Business Review and Sign-off | a |  | 3 | 2013-11-18 | 2013-11-20 |  |  | 2013-10-21 | 2013-11-20
1.2 | Infrastructure Readiness
1.2.1 | Development environment setup and Configuration |  | a | 5 | 2013-10-21 | 2013-10-25
1.2.2 | Test environment setup and configuration |  | a | 5 | 2013-10-21 | 2013-10-25
1.2.3 | UAT environment setup and configuration |  | a | 5 | 2013-10-21 | 2013-10-26
1.2.4 | Production environment setup and configurartion |  | a | 5 | 2013-10-21 | 2013-10-26 |  |  | 2013-10-21 | 2013-10-26
1.4 | Architecture and Design
1.4.1 | Baseline Architecture |  | a | 3 | 2013-11-19 | 2013-11-21
1.4.2 | Design |  | a | 4 | 2013-11-19 | 2013-11-22
1.4.3 | Conceptual Data Model |  | a | 4 | 2013-11-21 | 2013-11-26
1.4.4 | Logical and Physical Data Model |  | a | 5 | 2013-11-25 | 2013-11-30 |  |  | 2013-11-19 | 2013-11-30
1.4.5 | Business Review | a |  | 5 | 2013-12-02 | 2013-12-06
1.4.6 | Database Objects definition |  | a | 7 | 2013-12-02 | 2013-12-10
1.5 | Data Loads Design
1.5.1 | High Level Design |  | a | 4 | 2013-12-09 | 2013-12-12
1.6 | Analytics - Cubes Design
1.6.1 | High Level Design |  | a | 4 | 2013-12-09 | 2013-12-12 |  |  | 2013-12-02 | 2013-12-12
1.7 | Development - Data Loads (ETL)
1.7.1 | Low Level Design |  | a | 6 | 2013-12-13 | 2013-12-20
1.7.2 | Build for Source to Work area load |  | a | 3 | 2013-12-23 | 2013-12-25
1.7.3 | Build for Work area to Work History |  | a | 3 | 2013-12-26 | 2013-12-30
1.7.4 | Build for Work area to Staging |  | a | 4 | 2013-12-31 | 2014-01-03
1.7.5 | Build for Data Mart |  | a | 14 | 2014-01-06 | 2014-01-23
1.7.6 | Unit Testing |  | a | 25 | 2013-12-25 | 2014-01-28 |  |  | 2013-12-13 | 2014-01-28
1.8 | Development - Analytics ( Cubes )
1.8.1 | Low Level Design |  | a | 15 | 2013-12-13 | 2014-01-02
1.8.2 | Build Dimensions and Measures for the Cubes |  | a | 12 | 2014-01-09 | 2014-01-24
1.8.3 | Process Cubes and Unit testing |  | a | 6 | 2014-01-24 | 2014-01-31
| Modification of Reserve Model spreadsheet for Cube data extraction |  | a | 4 | 2014-01-28 | 2014-01-31 |  |  | 2013-12-13 | 2014-01-31
1.9 | Testing
1.9.1 | System and Integration Testing |  | a | 12 | 2014-01-30 | 2014-02-14 |  |  | 2014-01-30 | 2014-02-14
1.10 | UAT
1.10.1 | Deployment |  | a | 2 | 2014-02-17 | 2014-02-18
1.10.2 | Business testing | a |  | 8 | 2014-02-19 | 2014-02-28
1.10.3 | Business Sign-off | a |  | 8 | 2014-02-19 | 2014-02-28 |  |  | 2014-02-17 | 2014-02-28
1.11 | Production Deployment
1.11.1 | Configure, Deploy and Dry Run |  | a | 3 | 2014-03-03 | 2014-03-05
1.11.2 | GO Live |  | a | 1 | 2014-03-06 | 2014-03-06 |  |  | 2014-03-03 | 2014-03-06
215
Formulas:
Number of working days = NETWORKDAYS([Start],[End],1)
End = [Start]+4
End = [Start, row above]+4
Start = [Start, row above]
Start = [End, row above]
Actual Start = MIN(F8:[End])
Actual Start = MIN([Start]:[End])
Actual End = MAX(F8:[End])
Actual End = MAX([Start]:[End])

## Delivery Plan
High level Project Delivery Plan for BI/MI Strategic Program - Silver
|  | 2013-10-01 |  |  |  | 2013-11-01 |  |  |  | 2013-12-01 |  |  |  | 2013-01-01 |  |  |  | 2013-02-01 |  |  |  | 2013-03-01
WORK STREAMS
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
BIMI Strategic Project
Requirements Analysis (Detail)
Infrastructure Readiness
Database Design
Data warehouse Development
Data ETL (SSIS packages)
SSAS Cubes
Data Quality Management
Testing
UAT and Support
GO Live( PROD Configuration set up)
Support (Warranty)

## Sheet4 (hidden)
Process | type of work
Communication Process | Requirements Analysis (Detail)
Project Delivery Model | Requirements Analysis (Detail)
Requirements gathering and Analysis
Preparation | Requirements Analysis (Detail)
BRSD Preparation | Requirements Analysis (Detail)
Business Review and Sign-off | Requirements Analysis (Detail)
Infrastructure Readiness
Development environment setup and Configuration | Database Design
Test environment setup and configuration | Database Design
UAT environment setup and configuration | Database Design
Production environment setup and configurartion | Database Design
Architecture and Design
Baseline Architecture | Database Design
Design | Database Design
Conceptual Data Model | Database Design
Logical and Physical Data Model | Data warehouse Development
Business Review | Data warehouse Development
Database Objects definition & Data Mapping | Data warehouse Development
Data Loads Design
High Level Design | Data warehouse Development
Analytics - Cubes Design
High Level Design | Data warehouse Development
Development - Data Loads (ETL)
Low Level Design | Database ETL
Build for Source to Work area load | Database ETL
Build for Work area to Work History | Database ETL
Build for Work area to Staging | Database ETL
Build for Data Mart | Database ETL
Unit Testing | Database ETL
Development - Analytics ( Cubes )
Low Level Design | SSAS Cubes
Build Dimensions and Measures for the Cubes | SSAS Cubes
Process Cubes and Unit testing | SSAS Cubes
Modification of Reserve Model spreadsheet for Cube data extraction | SSAS Cubes
Testing
System and Integration Testing
UAT
Deployment
UAT Support
Business testing & Sign-off
Production Deployment
Configure, Deploy and Dry Run
GO Live

## Sheet5
|  |  | OCT | [22 empty] | Nov
|  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 1 |  |  |  |  | 2
| WORK STREAMS | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | m | t | w | th | f | S | SU | m | t | w | th | f | S | SU | m | t | w | th | f | S | SU | m | t | w | th | f | S | SU | m | t | w | th | f | S | SU | m | t | w | th | f | S | SU | m | t | w | th | f | S | SU
|  | 30 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 25 | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
BIMI Strategic Project
Requirements Analysis (Detail)
Infrastructure Readiness
Database Design
Data warehouse Development
Data ETL (SSIS packages)
SSAS Cubes
Data Quality Management
Testing
UAT and Support
GO Live( PROD Configuration set up)
Support (Warranty)