## TM1
BI/MI TM1
Project Plan: | Work Breakdown Structure View
Start Date: | 2013-10-07
End Date: | 2014-02-20
S.No. | Tasks | Responsibility |  | Number of working days | Start | End | % Complete | Dependency | Actual Start | Actual End | Remarks | Remarks
|  | PH | TCS
1.1 | Process
1.1.1 | Communication Process | a |  | 5 | 2013-10-07 | 2013-10-11
1.1.2 | Project Delivery Model | a |  | 5 | 2013-10-07 | 2013-10-11 | 100%
1.2 | Infrastructure Readiness
1.2.1 | Development environment setup and Configuration |  | a | 5 | 2013-10-07 | 2013-10-11
1.2.2 | Test environment setup and configuration |  | a | 5 | 2013-10-07 | 2013-10-11
1.2.3 | UAT environment setup and configuration |  | a | 6 | 2013-10-07 | 2013-10-11
1.2.4 | Production environment setup and configurartion |  | a | 6 | 2013-10-07 | 2013-10-11
1.3 | Requirements gathering and Analysis
1.3.1 | Preparation | a | a | 14 | 2013-10-14 | 2013-10-31
1.3.2 | BRSD Preparation |  | a | 6 | 2013-10-28 | 2013-11-04
1.3.3 | Business Review and Sign-off | a |  | 3 | 2013-11-04 | 2013-11-06
1.4 | Architecture and Design
1.4.1 | Baseline Architecture |  | a | 3 | 2013-11-05 | 2013-11-07
1.4.2 | Design |  | a | 3 | 2013-11-05 | 2013-11-08
1.4.3 | Conceptual Data Model |  | a | 3 | 2013-11-07 | 2013-11-12
1.4.4 | Logical and Physical Data Model |  | a | 5 | 2013-11-11 | 2013-11-16
1.4.5 | Business Review | a |  | 5 | 2013-11-18 | 2013-11-22
1.4.6 | Database Objects definition & Data Mapping |  | a | 7 | 2013-11-18 | 2013-11-26
1.5 | Data Loads Design
1.5.1 | High Level Design |  | a | 3 | 2013-11-25 | 2013-11-28
1.6 | Analytics - Cubes Design
1.6.1 | High Level Design |  | a | 3 | 2013-11-25 | 2013-11-28
1.7 | Development - Data Loads (ETL)
1.7.1 | Low Level Design |  | a | 11 | 2013-11-29 | 2013-12-06
1.7.2 | Build for Source to Work area load |  | a | 4 | 2013-12-09 | 2013-12-11
1.7.3 | Build for Work area to Work History |  | a | 4 | 2013-12-12 | 2013-12-16
1.7.4 | Build for Work area to Staging |  | a | 10 | 2013-12-17 | 2013-12-20
1.7.5 | Build for Data Mart |  | a | 30 | 2013-12-23 | 2014-01-09
1.7.6 | Unit Testing |  | a | 25 | 2013-12-11 | 2014-01-14
1.8 | Development - Analytics ( Cubes )
1.8.1 | Low Level Design |  | a | 15 | 2013-11-29 | 2013-12-19
1.8.2 | Build Dimensions and Measures for the Cubes |  | a | 25 | 2013-12-26 | 2014-01-10
1.8.3 | Process Cubes and Unit testing |  | a | 15 | 2014-01-10 | 2014-01-17
1.9 | Testing
1.9.1 | System and Integration Testing |  | a | 34 | 2014-01-16 | 2014-01-31
1.10 | UAT
1.10.1 | Deployment |  | a | 2 | 2014-02-03 | 2014-02-04
| UAT Support |  | a | 8 | 2014-02-05 | 2014-02-14
1.10.2 | Business testing & Sign-off | a |  | 8 | 2014-02-05 | 2014-02-14
1.11 | Production Deployment
1.11.1 | Configure, Deploy and Dry Run |  | a | 3 | 2014-02-17 | 2014-02-19
1.11.2 | GO Live |  | a | 1 | 2014-02-20 | 2014-02-20
Formulas:
Number of working days = NETWORKDAYS([Start],[End],1)
End = [Start]+4
End = [Start, row above]+4
Start = [Start, row above]
Start = [End, row above]